## Feuil1
Estimates for Phase 3A Frontend Tasks
Feature | Task | Estimate | Sprint 1A | Sprint 1B | Sprint 2
Reworking UI & dynamic quest flow
| Analysis, desing & estimates | 8 | 8 | 0 | 0
| Word Unscrambling mechanic & UI | 3 | 0 | 3 | 0
| Word Crafting mechanic & UI | 3 | 0 | 3 | 0
| Sentence Decrypting mechanic & UI | 3 | 0 | 3 | 0
| Sentence Unscrambling mechanic & UI | 3 | 0 | 3 | 0
| Activity selection hub | 8 | 0 | 8 | 0
| Quest rescripting | 2 | 0 | 2 | 0
| Feedbacks & improvements | 8 | 0 | 8 | 0
| Total | 38 | 8 | 30 | 0
Applying general comments
| Analysis, design & estimates | 4 | 4 | 0 | 0
| Floating letter overlap issue | 2 | 0 | 2 | 0
| Remove "click to continue" | 1 | 0 | 0 | 1
| VO overlap handling system | 3 | 0 | 0 | 3
| "feed me" mini VO | 1 | 0 | 0 | 1
| Sentence "jump to life" anim | 2 | 0 | 2 | 0
| Click auto-send for floating letters | 2 | 0 | 2 | 0
| Click auto-eat/burp for words in tray | 2 | 0 | 2 | 0
| Exploded words returning its letters to gameplay area | 2 | 0 | 0 | 2
| Funny anim when feeding flier to Mini | 2 | 0 | 0 | 2
| Larger characters by 33% in The Lab | 1 | 0 | 0 | 1
| Improving padding, margin, kerning, etc. | 4 | 0 | 4 | 0
| Letter name VO | 1 | 0 | 0 | 1
| Various fixes to VO and quest | 2 | 0 | 0 | 2
| Displaying the player's "portrait" under the dialog box | 2 | 0 | 0 | 2
| Total | 31 | 4 | 12 | 15
Wild Lucu Taming mechanic
| Analysis, design & estimates | 8 | 8 | 0 | 0
| Letter Pattern Cards reward popup | 2 | 2 | 0 | 0
| Letter Pattern Cards selection popup | 2 | 2 | 0 | 0
| Wild Lucu Taming mechanic | 12 | 0 | 0 | 12
| Wild Lucu Taming reward popup | 1 | 0 | 0 | 1
| Intelligent Inventory | 8 | 0 | 0 | 8
| Add The Forest to navigation popup and level system | 1 | 0 | 0 | 1
| Saving quest progress and activity states to enable navigation at-will | 8 | 0 | 0 | 8
| Quest rescripting | 4 | 0 | 0 | 4
| Feedbacks & improvements | 16 | 0 | 0 | 16
| Total | 62 | 12 | 0 | 50
Total |  | 131 | 24 | 42 | 65
Budget |  | 136 | 24 | 42 | 70
Note on D4: sbouchard: The total amount of time required for a task
Note on E4: sbouchard: The time already spent during Sprint 1
Note on F4: sbouchard: The remaining time required during Sprint 1
Note on G4: sbouchard: The time required during Sprint 2